## Product_Backlog
Product Name: RRS_GUI
Team ID:

Name: Emmanuel Barragan
Initials: EB
Student ID: 1000921049

(Additional names for teams only)
Name:
Initials:
Student ID:

Name:
Initials:
Student ID:

Name:
Initials:
Student ID:

Total Features	12	Status	Sprint Ends
Sprint 1 Left	12	Completed	Oct 06
Sprint 2 Left	12	Completed	Oct 13
Sprint 3 Left	8	Completed	Oct 20
Sprint 4 Left	8	Due	Oct 27
Sprint 5 Left	8	Due	Nov 03
Sprint 6 Left	8	Due	Nov 10
Sprint 7 Left	8	Due	Nov 17
Sprint 8 Left	8	Due	Nov 22

					Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
					Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID	Prio	Status	Sprint #	Team Size	As a...	I want to...	So that...	Notes
	1			1	All	open a GUI main window	I can interact with RRS Manager with my mouse	No menu required here – run program, create a part
	2			1	PM	create robot parts	I can define robot models	No menu required here – run program, create a part
	3			1	PM	create robot parts via GUI dialogs	I can define robot models	An fl_input centric approach is OK initially, but a custom dialog is worth bonus points (perhaps Create > Robot Part)
	4			1	PM	define new robot models	RRS can sell them to our Beloved Customers	Menu needed – create parts, then create a robot model
	5			1	PM	define new robot models via GUI dialogs	RRS can sell them to our Beloved Customers	Similar to robot parts (perhaps Create > Robot Model)
	6			1	BC	browse a catalog of robots	I can buy one or more robots	Need to list robots models, then list parts in selected model
	7			1	BC	browse a catalog of robots via a GUI report	I can buy one or more robots	A text output is OK initially, but an attractive HTML-like output is desired (perhaps (Report > All Robot Models)
	8			1	BC	see pictures of the robots in the GUI catalog	I can see what I'm buying	Add picture when defining robot model, and show it in the robot model report
	9			1	SA	create a robot order for a Customer	I can sell robots and thus do my job well	Select robot model and quantity, show details with total price
	10			1	PB	Create a new Beloved Customer via GUI	I can keep track of who's buying our products	The usual name, address, phone number, and email address (perhaps Create > Customer)
	11			1	PB	Create a new Sales Associate via GUI	I can keep track of my employees' performance	Name and employee number at a minimum (perhaps Create > Sales Associate)
	12			1	SA	Create a robot order for a Customer via GUI	I can sell robots and thus do my job well
Product Backlog Burn Chart
Features Remaining at Start of Sprint
Sprints

## Sprint_4_Backlog
Sprint #4					*** Example Only – Set up a tab for EACH SPRINT ***
Start on
End on
Demo on

Total Tasks	1
Day 1 Left	1
Day 2 Left	1
Day 3 Left	1
Day 4 Left	1
Day 5 Left	1
Day 6 Left	1
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
				EB	Study for test
Sprint Burn Chart
Days
Tasks

## Sprint_5_Backlog
Sprint #5					*** Example Only – Set up a tab for EACH SPRINT ***
Start on
End on
Demo on

Total Tasks	1
Day 1 Left	1
Day 2 Left	1
Day 3 Left	1
Day 4 Left	1
Day 5 Left	1
Day 6 Left	1
Day 7 Left	1

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
				EB	Create GUI main window
Sprint Burn Chart
Days
Tasks